## Report
Blue Team | Project Name: Roomy System (RS) |  |  | Test Designed by: Blue team
| Module Name: Report |  |  | Test Designed date: 10/11/2018
| Release Version: v1.0 |  |  | Test Execution date: 10/11/2018
Test Executed by: Huynh Vu Ha Lan
Test case id | Test cases | Preconditions | Input test data | Steps to be executed | Expected results | Actual results | Pass/fail | Status
TC_REPORT01 | Report an accomodation was rented | TC_VA01 |  | 1) Open browser 2) Type the link: 3) Click on "Đã có người thuê" option. 4) Click on "Gửi" button | The screen displays "Báo cáo của bạn đã được gởi đi." message box. | The screen displays detail of accommodation. | Fail | Fixed Close
TC_REPORT02 | Report about false information of accomodation | TC_VA01 |  | 1) Open browser 2) Type the link: 3) Click on "Sai thông tin" option. 4) Click on "Gửi" button | The screen displays "Báo cáo của bạn đã được gởi đi." message box. | The screen displays detail of accommodation. | Fail | Fixed Close
TC_REPORT03 | Report about an accomodation has intermediary services | TC_VA01 |  | 1) Open browser 2) Type the link: 3) Click on "Dịch vụ trung gian" option. 4) Click on "Gửi" button | The screen displays "Báo cáo của bạn đã được gởi đi." message box. | The screen displays detail of accommodation. | Fail | Fixed Close

## Acceptance
Blue Team | Project Name: Roomy System (RS) |  | Test Designed by: Blue team
| Module Name: Acceptance |  | Test Designed date: 10/11/2018
| Release Version: v1.0 |  | Test Execution date: 10/11/2018
Test Executed by: Huynh Vu Ha Lan
Test case id | Test cases | Preconditions | Input test data | Steps to be executed | Expected results | Actual results | Pass/fail | Status
TC_A01 | View exactly information | TC_BR01 and TC_VLOR01 | None | Click on button in "Chi tiết" columm | Browser to view excatly information about name, e-mail, phone number and message of renter | Browser to view excatly information about name, e-mail, phone number and message of renter | Pass | Close
TC_A02 | "Đồng ý" button | TC_A01 | 1) "Giá": '1000000' 2) "Ngày bắt đầu": '05/12/2018' 3) "Ngày kết thúc": '05/3/2019' | 1) Enter the infomation for that contract 2) Click on "Đồng ý" button | Screen displays "Bạn đã cho thuê chỗ ở thành công". The status of that accommodation is set at "Đã thuê". Database save that contract information with the price and date landlord entered | The status of that accommodation is set at "Đã thuê". Database save that contract information with the price landlord entered | Fail | Open
TC_A03 | "Từ chối" button | TC_A01 | None | Click on "Từ chối" button | Screen displays "Bạn đã hủy hợp đồng này" | Screen displays "Bạn đã hủy hợp đồng này" | Pass | Close
TC_A04 | Expired contract | TC_BR01 | None | None | If a booking didn't accept after 48 hours, it will be automatically cancel by system. | If a booking didn't accept after 48 hours, it will be automatically cancel by system. | Pass | Close
TC_A05 | Haven't booking | TC_VLOR01 | None | Click on button in "Chi tiết" columm | Browser to view "Chưa có ai đặt phòng" | Browser to view "Chưa có ai đặt phòng" | Pass | Close
TC_A06 | "Kết thúc sớm" button | TC_A02 | None | Click on "Kết thúc sớm" button | The status of that accommodation is set at "Còn trống" | The status of that accommodation is set at "Còn trống" | Pass | Close

## Manage reports
Blue Team | Project Name: Roomy System (RS) |  | Test Designed by: Blue team
| Module Name: Manage reports |  | Test Designed date: 10/11/2018
| Release Version: v1.0 |  | Test Execution date: 10/11/2018
Test Executed by: Huynh Vu Ha Lan
Test case id | Test cases | Preconditions | Input test data | Steps to be executed | Expected results | Actual results | Pass/fail | Status
TC_MR01 | View list of user reports | TC_REPORT01 and TC_LFA01 | None | Click on "Quản lí báo cáo" item | View all user reports | View all user reports | Pass | Close
TC_MR02 | View detail of a report | TC_MR01 | None | Click on button in "Chi tiết" columm | View axactly information of report | Error 404 | Fail | Open
TC_MR03 | Delete a report | TC_MR01 | None | Click on button in "Xóa" columm | The screen displays "Đã xóa báo cáo" and the browser to view list of reports without the report was deleted | The browser to view list of reports without no change | Fail | Open
TC_MR04 | "Trang trước" button | TC_MR01 | None | Click on "Trang trước' button | The browser to view previous page of list without includes the reports wich have in current page. If the current page is the first page or the list has one page, the browser to view that page. | The browser to view previous page of list without includes the reports wich have in current page. If the current page is the first page or the list has one page, the browser to view that page. | Pass | Close
TC_MR05 | "Trang sau" button | TC_MR01 | None | Click on "Trang sau' button | The browser to view next page of list without includes the reports wich have in current page. If the current page is the last page or the list has one page, the browser to view that page. | The browser to view next page of list without includes the reports wich have in current page. If the current page is the last page or the list has one page, the browser to view that page. | Pass | Close
TC_MR06 | There are not any report | TC_LFA01 | None | Click on "Quản lí báo cáo" item | If there are not any report in that time, the screen displays "Chưa có báo cáo nào". | If there are not any report in that time, the screen displays "Chưa có báo cáo nào". | Pass | Close

## Manage users
Blue Team | Project Name: Roomy System (RS) |  | Test Designed by: Blue team
| Module Name: Manage users |  | Test Designed date: 10/11/2018
| Release Version: v1.0 |  | Test Execution date: 10/11/2018
Test Executed by: Huynh Vu Ha Lan
Test case id | Test cases | Preconditions | Input test data | Steps to be executed | Expected results | Actual results | Pass/fail | Status
TC_MU01 | View list of user users | TC_R01 and TC_LFA01 | None | Click on "Quản lí người dùng" item | View all user users | View all user users | Pass | Close
TC_MU02 | View detail of a users | TC_MU01 | None | Click on button in "Chi tiết" columm | View axactly information of user | Error 404 | Fail | Open
TC_MU03 | Delete a user | TC_MU01 | None | Click on button in "Xóa" columm | The screen displays "Đã xóa tài khoản" and the browser to view list of users without the user was deleted | The browser to view list of users without no change | Fail | Open
TC_MU04 | "Trang trước" button | TC_MU01 | None | Click on "Trang trước' button | The browser to view previous page of list without includes the users wich have in current page. If the current page is the first page or the list has one page, the browser to view that page. | The browser to view previous page of list without includes the users wich have in current page. If the current page is the first page or the list has one page, the browser to view that page. | Pass | Close
TC_MU05 | "Trang sau" button | TC_MU01 | None | Click on "Trang sau' button | The browser to view next page of list without includes the users wich have in current page. If the current page is the last page or the list has one page, the browser to view that page. | The browser to view next page of list without includes the users wich have in current page. If the current page is the last page or the list has one page, the browser to view that page. | Pass | Close
TC_MU06 | There are not any report | TC_MU01 | None | Click on "Quản lí người dùng" item | If there are not any report in that time, the screen displays "Chưa có người dùng nào". | If there are not any report in that time, the screen displays "Chưa có người dùng nào". | Pass | Close

## Manage accommodations for admin
Blue Team | Project Name: Roomy System (RS) |  | Test Designed by: Blue team
| Module Name: Manage accommodations for admin |  | Test Designed date: 10/11/2018
| Release Version: v1.0 |  | Test Execution date: 10/11/2018
Test Executed by: Huynh Vu Ha Lan
Test case id | Test cases | Preconditions | Input test data | Steps to be executed | Expected results | Actual results | Pass/fail | Status
TC_MAFA01 | View list of accommodations | TC_AZ01 and TC_LFA01 | None | Click on "Quản lí Cho thuê" item | View all zones | View all zones | Pass | Close
TC_MAFA02 | View detail of a accommodations | TC_MAFA01 | None | Click on button in "Chi tiết" columm | View axactly information of zone | Error 404 | Fail | Open
TC_MAFA03 | Delete a zone | TC_MAFA01 | None | Click on button in "Xóa" columm | The screen displays "Đã xóa báo cáo" and the browser to view list of zones without the zone was deleted | The browser to view list of zones without no change | Fail | Open
TC_MAFA04 | "Trang trước" button | TC_MAFA01 | None | Click on "Trang trước' button | The browser to view previous page of list without includes the zones wich have in current page. If the current page is the first page or the list has one page, the browser to view that page. | The browser to view previous page of list without includes the zones wich have in current page. If the current page is the first page or the list has one page, the browser to view that page. | Pass | Close
TC_MAFA05 | "Trang sau" button | TC_MR01 | None | Click on "Trang sau' button | The browser to view next page of list without includes the zones wich have in current page. If the current page is the last page or the list has one page, the browser to view that page. | The browser to view next page of list without includes the zones wich have in current page. If the current page is the last page or the list has one page, the browser to view that page. | Pass | Close
TC_MAFA06 | There are not any zones | TC_LFA01 | None | Click on "Quản lí Cho thuê" item | If there are not any zones in that time, the screen displays "Chưa có khu nào". | If there are not any zones in that time, the screen displays "Chưa có khu nào". | Pass | Close

## Statistical
Blue Team | Project Name: Roomy System (RS) |  | Test Designed by: Blue team
| Module Name: Statistical |  | Test Designed date: 10/11/2018
| Release Version: v1.0 |  | Test Execution date: 10/11/2018
Test Executed by: Huynh Vu Ha Lan
Test case id | Test cases | Preconditions | Input test data | Steps to be executed | Expected results | Actual results | Pass/fail | Status
TC_St01 | The room's chart and user's chart | TC_LFA01 | None | Click on "Thống kê" item | The browser to view exactly charts base on data | The browser to view exactly charts base on data | Pass | Close
TC_St02 | "Khu" item | TC_LFA01 | None | Click on "Khu" item | The browser to view exactly sum of zones. After click on "Khu" item, the browser to continue at TC_MAFA01. | The browser to view exactly sum of zones. After click on "Khu" item, the browser to continue at TC_MAFA01. | Pass | Close
TC_St03 | "Báo cáo" item | TC_LFA01 | None | Click on "Báo cáo" item | The browser to view exactly sum of reports. After click on "Báo cáo" item, the browser to continue at TC_MR01. | The browser to view exactly sum of reports. After click on "Báo cáo" item, the browser to continue at TC_MR01. | Pass | Close
TC_St04 | "Người dùng" item | TC_LFA01 | None | Click on "Người dùng" item | The browser to view exactly sum of reports. After click on "Người dùng" item, the browser to continue at TC_MU01. | The browser to view exactly sum of reports. After click on "Người dùng" item, the browser to continue at TC_MU01. | Pass | Close

## Creat an admin account
Blue Team | Project Name: Roomy System (RS) |  | Test Designed by: Blue team
| Module Name: Creat an admin account |  | Test Designed date: 10/11/2018
| Release Version: v1.0 |  | Test Execution date: 10/11/2018
Test Executed by: Huynh Vu Ha Lan
Test case id | Test cases | Preconditions | Input test data | Steps to be executed | Expected results | Actual results | Pass/fail | Status
TC_CAA01 | Creat an account with valid value | TC_LFA01 | 1) "E-mail đăng nhập": 'huynhvuhalan@gmail.com 2) "Mật khẩu": '1234abcd' 3) "Xác nhận mật khẩu": '1234abcd' | 1) Click on "Tạo tài khoản quản trị viên" 2) Enter the information for boxes 3) Click on "Tạo tài khoản". | The screen displays "Đã tạo tài khoản admin thành công". That account is saved in database and can use to log in the admin role of the system. | None | Fail | Not run
TC_CAA02 | Creat an account with invalid e-mail | TC_LFA01 | 1) "E-mail đăng nhập": 'huynhvuhalangmail.com 2) "Mật khẩu": '1234abcd' 3) "Xác nhận mật khẩu": '1234abcd' | 1) Click on "Tạo tài khoản quản trị viên" 2) Enter the information for boxes 3) Click on "Tạo tài khoản". | The screen displays "E-mail phải chưa kí tự '@'" | None | Fail | Open
TC_CAA03 | Creat an account with e-mail contains special characters | TC_LFA01 | 1) "E-mail đăng nhập": 'h^uynhvuhalan@gmail.com 2) "Mật khẩu": '1234abcd' 3) "Xác nhận mật khẩu": '1234abcd' | 1) Click on "Tạo tài khoản quản trị viên" 2) Enter the information for boxes 3) Click on "Tạo tài khoản". | The screen displays "E-mail không chứa kí tự '^'" | None | Fail | Open
TC_CAA04 | Creat an account without e-mail | TC_LFA01 | 1) "E-mail đăng nhập": Empty 2) "Mật khẩu": '1234abcd' 3) "Xác nhận mật khẩu": '1234abcd' | 1) Click on "Tạo tài khoản quản trị viên" 2) Enter the information for boxes 3) Click on "Tạo tài khoản". | The screen displays "Chưa nhập e-mail" | None | Fail | Open
TC_CAA05 | Creat an account with invalid password | TC_LFA01 | 1) "E-mail đăng nhập": Empty 2) "Mật khẩu": '1234' 3) "Xác nhận mật khẩu": '1234' | 1) Click on "Tạo tài khoản quản trị viên" 2) Enter the information for boxes 3) Click on "Tạo tài khoản". | The screen displays "Mật khẩu phải có nhiều hơn 5 kí tự và ít hơn 20 kí tự" | None | Fail | Open
TC_CAA06 | Creat an account with e-mail was exist in system | TC_LFA01 | 1) "E-mail đăng nhập": 'huynhvuhalan.97@gmail.com 2) "Mật khẩu": '1234abcd' 3) "Xác nhận mật khẩu": '1234abcd' | 1) Click on "Tạo tài khoản quản trị viên" 2) Enter the information for boxes 3) Click on "Tạo tài khoản". | The screen displays "E-mail đã tồn tại" | None | Fail | Open
TC_CAA07 | Creat an account without password | TC_LFA01 | 1) "E-mail đăng nhập": 'huynhvuhalan@gmail.com 2) "Mật khẩu": Empty 3) "Xác nhận mật khẩu": '1234abcd' | 1) Click on "Tạo tài khoản quản trị viên" 2) Enter the information for boxes 3) Click on "Tạo tài khoản". | The screen displays "Mật khẩu phải có nhiều hơn 5 kí tự và ít hơn 20 kí tự" | None | Fail | Open
TC_CAA08 | Creat an account without authentication password | TC_LFA01 | 1) "E-mail đăng nhập": 'huynhvuhalan@gmail.com 2) "Mật khẩu": '1234abcd' 3) "Xác nhận mật khẩu": Empty | 1) Click on "Tạo tài khoản quản trị viên" 2) Enter the information for boxes 3) Click on "Tạo tài khoản". | The screen displays "Mật khẩu phải có nhiều hơn 5 kí tự và ít hơn 20 kí tự" | None | Fail | Open
TC_CAA09 | Creat an account with authentication password different from password | TC_LFA01 | 1) "E-mail đăng nhập": 'huynhvuhalan@gmail.com 2) "Mật khẩu": '1234abcd' 3) "Xác nhận mật khẩu": '1234abcc' | 1) Click on "Tạo tài khoản quản trị viên" 2) Enter the information for boxes 3) Click on "Tạo tài khoản". | The screen displays "Mật khẩu không khớp" | None | Fail | Open

## Modul report
Test Report
Project Name | Roomy System Management |  | Creator |  | Huynh Vu Ha Lan
Date | 29/11/2018 |  | Reviewer/Approver
No | Module Name | Pass | Fail | Not Run | N/A | Number of test cases
1 | Report | 0 | 3 | 0 | 0 | 3
2 | Acceptance | 5 | 1 | 0 | 0 | 6
4 | Manage reports | 4 | 2 | 0 | 0 | 6
5 | Manage users | 5 | 1 | 0 | 0 | 6
6 | Manage accommodations for admin | 4 | 2 | 0 | 0 | 6
7 | Statitiscal | 4 | 0 | 0 | 0 | 4
8 | Create an admin account | 0 | 0 | 9 | 0 | 9
| Total | 22 | 9 | 9 | 0 | 40
| Test coverage | 5500%